## Re-Opening Plan
BAM Draft Re-Opening Plan - Boise Art Museum
Based on national art museum best practices, Governor's guidelines, CDC recommendations - subject to change
To participate in protecting public health BAM has been closed to the public since March 16. In the interest of ensuring the
wellbeing of our staff, volunteers, and visitors, we are implementing guidelines to re-open following CDC and Health Department recommendations.
The Plan informs the BAM community about plans for staff and visitors to return to the Museum and our measures for providing a safe and healthy environment.
May 4 - May 15 | Governor's Stage 1 | May 16 - May 29 - Stage 2 | May 30 - June 12 - Stage 3 | June 13 - June 26 - Stage 4 | 2020-07-01 | Next 3 months
| Businesses Re-open with distancing and sanitation protocols | *
| Gatherings should be avoided | Gatherings of fewer than 10 people allowed | Gatherings up to 50 people allowed | Gatherings of more than 50 people allowed
| Daycares, organized youth activities, camps can open | Indoor gyms can open | * | Theaters, sporting venues, bars can open
| Engage in physical distancing of 6 feet | * | * | *
| Wear face coverings in public places | * | * | *
| Stay home if sick | * | * | *
| Practice good hand washing hygiene | * | * | *
| Cover coughs and sneezes | * | * | *
| Disinfect surfaces and objects regularly | * | * | *
May 1 - May 30 |  |  | May 30 - June 14 | June 15 - June 26
BAM's Stages
HEALTH AND SAFETY FIRST
Staff Return | Phased - BAM has room for physical distancing, personal protections and sanitation
| Rotating shifts - no more than 8 people - (see schedule) | Staff returns for full-time shifts with physical distancing
Staff will not eat together
| Resume enhanced disinfecting protocols that were implemented in March (office & some public areas) |  | Resume enhanced disinfecting protocols for all areas of Museum
door knobs, hand rails, counters, touch samples - wipe front door handles in/outside
Provide hand-sanitizer for staff, especially front-end/admissions staff
| Staff may wear masks in office and must wear in public spaces once open (may need to be removed for telephone/conference calls) |  | Admissions staff/VSA's wear masks/gloves | Admissions staff/VSA's wear masks/gloves
Confidential staff temperature log kept daily
In-person Meetings only if staff can maintain 6 feet of distance (meet in larger spaces such as education studios)
Staff must call in sick if they are unwell - PTO applies to general sick leave
Staff who are uncomfortable returning to work may request PTO. If no PTO, may request leave without pay
Not accepting visitors/outside workers into building except as essential with approval - keep a log (discuss)
fire, security, electrical, plumbing, water delivery, mail delivery
Increased reporting requirements related to calling in sick(example: contact info for CDC reporting, if required, symptoms, test results, written diagnosis, doctor's notes, etc.)
Ensure staff has proper tools/materials to do jobs safely
Review emergency manual and protocols with all staff prior to June 5, discuss any required changes based on COVID-19
Facilities | Purchase and install 1 new self-swipe credit card processor for admissions
Purchase and install 2 sneeze guards for admissions and store
| Purchase and install 2 non-touch hand-sanitizing stations (admissions, sculpture court at entry to Nelson Gallery) |  | AEGallery closed | AEGallery open with touchables removed
if back-ordered, use hand sanitizer bottles until received
Purchase 3 infrared thermometers (admissions, education, office)
Purchase 2 number flip charts for tracking people leaving to always show # of people
Keep hand-washing signs in bathrooms
Replace manual soap dispensers with hands-free versions
Janitorial considerations - self-hire employees rather than going back to janitorial contract
Wrap public drinking fountain and place signage on wall
Visitors | No visitors |  | June 5 - BAM opens for up to 50 visitors during public hours | June 15 - up to 125 visitors during public hours
Per the national standard for art museums, based on our square footage, BAM can allow up to 125 people in the exhibition spaces and still maintain the required level of social distancing
| 16,000 sq. ft. – 10%, 6-ft. radius, 113.1 sq. ft. per person. |  | Potential reservations for June 2-4 for members only - join to visit
476 sq. ft. store - 10%, 6-ft. radius, 113.1 sq. ft. per person = 4/5 shoppers, max.
| Information Requirements (name, phone, email of visitors for potential CDC reporting) |  | can require temperatures (will not be doing routinely)
| Do not re-use handouts, maps, etc. once a visitor has touched - make public recycling bins |  | can require contact information (name, phone number, email)
| Do not make reservations for large groups to visit BAM together |  | can require mask - provide or turn away
| Look at and implement the ability to purchase tickets online in advance to limit money handling transactions |  | can turn away if exhibiting unwell symptoms
Volunteers | 0 volunteers | 0 volunteers | 0 volunteers | Volunteers follow same protocols as staff
establish protocols for return of volunteers
EXHIBITIONS | Some exhibitions will be canceled, postponed, extended
Consider when installing new exhibitions, have fewer artworks to encourage physical distancing
Check technology in all exhibitions prior to re-open days
PROGRAMS | 0 - suspend, hold virtually, or provide resources | 0 - suspend, hold virtually, or provide resources
ArtReach
School tours
Docent training
| Camps/Classes for children |  | Camps/Classes for Children - depends on enrollment, protocols, instructors
Workshops for Adults
| Summer Teacher Institutes |  | Virtual Classes for Teachers?
Monthly Programs
Especially for Seniors
Toddler Wednesday
Hands-On Saturday
| First Thursday |  | No First Thursday in June
Draw Inspiration
No regularly scheduled monthly programs in June
FACILITY RENTAL | 0 |  |  | rental events may resume after hours
DIGITAL/VIRTUAL PROGRAMMING
Continue with digital offerings through closure, and potentially beyond in a planned-in-advance manner
Consider other methods of delivery for programs during and beyond closure to serve larger population
INTERNAL/EXTERNAL COMMUNICATIONS
website
doors
inside building - reminders for hand hygiene, no hand-shaking, physical distancing
e-blasts
social media
board
staff
school teachers
instructors
registrants
visitors
Proactively communicate precautions, social distancing, visitor registration and temps if required
Pre-empt and manage expectations of visitors, participants and partners
Personal details may be required
May be delays or inconveniences as a result of visitor registration, if required
Persons who seem unwell may be turned away
Visitors may need to wait for others to leave to maintain occupancy limited related to physical distancing
Programs/Events may be canceled or postponed, or venue closed, possibly with short notice
Encourage visitors, participants, partners, staff to stick to the facts about COVID-19 and to avoid related rumors, unscientific information, stigmatism and discrimination.
Prepare marketing plan to begin to attract audiences again
Statement: Art museums will play a vital role in our nation's recovery from the pandemic.
With the health and safety of our visitors and staff as our highest priority, BAM is planning to re-open
in accordance with national and local guidelines and conditions. We continue to
monitor this situation regularly and will update our website and social media channels with a re-opening
date as soon as one is determined.
Discuss tension points of new realities with staff on regular basis

## Schedule
Two shifts 8 - noon, 12:30 - 4:30 |  |  | If essential work requires longer shifts, request approval from Melanie
janitorial and building work 8 - 9:30 |  |  | Take care of food needs prior to and after 4-hr shifts. |  |  | FT
|  |  | If bring food for break, do not eat with others, take garbage out |  |  | Melanie
May 4-8 | Monday | Tuesday | Wednesday | Thursday | Friday | Caren
1 | Todd | Todd | Todd | Todd | Todd | Hana
2 | Melanie | Melanie | Melanie | Melanie | Melanie | Mackenzie
3 | Caren | Caren |  | Caren | Caren | Skye
4 | Deanna | Deanna | Deanna | Deanna | Deanna | Todd
5 | Skye | Skye | Skye |  | Skye | Britney
6 | Nora | Nora | Nora | Nora | Nora | Rebecca
7 | Rebecca | Rebecca | Rebecca | Rebecca | Rebecca | Andrea
Emily
Deanna
1 | Melanie | Melanie | Melanie | Melanie | Melanie | Nora
2 | Caren | Caren | Caren | Caren | Caren | Mark
3 | Hana | Hana | Hana | Hana | Hana | Sam
4 | Britney | Britney | Britney | Britney | Britney | Lemuel
5 | Andrea | Andrea | Andrea | Andrea | Andrea | Lexie
6 | Emily | Emily | Emily | Emily | Emily | Jace
7 | Mackenzie | Mackenzie | Mackenzie | Mackenzie | Mackenzie | Caitlyn
8 |  |  |  | Skye |  | Corissa
May 11-15 | Monday | Tuesday | Wednesday | Thursday | Friday
1 | Todd | Todd |  | Todd | Todd
2 | Melanie | Melanie | Melanie | Melanie | Melanie
3 | Caren | Caren | Caren | Caren | Caren
4 | Hana | Hana | Hana | Hana | Hana
5 | Mackenzie | Mackenzie | Mackenzie | Mackenzie | Mackenzie
6 | Deanna | Deanna | Deanna | Deanna | Deanna
7 | Nora | Nora | Nora | Nora | Nora
1 | Melanie | Melanie | Melanie | Melanie | Melanie
2 | Caren | Caren | Caren | Caren | Caren
3 | Britney | Britney | Britney | Britney | Britney
4 | Andrea | Andrea | Andrea | Andrea | Andrea
5 | Emily | Emily | Emily | Emily | Emily
6 | Skye | Skye | Skye | Skye | Skye
7 | Rebecca | Rebecca | Rebecca | Rebecca | Rebecca
8 |  |  | Todd
May 18 - return to full-day schedules unless new news from governor, then:
May 18-22 | Monday | Tuesday | Wednesday | Thursday | Friday
1 | Todd | Todd | Todd | Todd | Todd
2 | Melanie | Melanie | Melanie | Melanie | Melanie
3 | Caren | Caren | Caren | Caren | Caren
4 | Britney | Britney | Britney | Britney | Britney
5 | Mackenzie | Mackenzie | Mackenzie | Mackenzie | Mackenzie
6 | Emily | Emily | Emily | Emily | Emily
7 | Skye | Skye | Skye | Skye | Skye
1 | Melanie | Melanie | Melanie | Melanie | Melanie
2 | Caren | Caren | Caren | Caren | Caren
3 | Hana | Hana | Hana | Hana | Hana
4 | Andrea | Andrea | Andrea | Andrea | Andrea
5 | Deanna | Deanna | Deanna | Deanna | Deanna
6 | Nora | Nora | Nora | Nora | Nora
7 | Rebecca | Rebecca | Rebecca | Rebecca | Rebecca
May 25-29 | Monday | Tuesday | Wednesday | Thursday | Friday
1 | Todd | Todd | Todd | Todd | Todd
2 | Melanie | Melanie | Melanie | Melanie | Melanie
3 | Caren | Caren | Caren | Caren | Caren
4 | Hana | Hana | Hana | Hana | Hana
5 | Andrea | Andrea | Andrea | Andrea | Andrea
6 | Nora | Nora | Nora | Nora | Nora
7 | Rebecca | Rebecca | Rebecca | Rebecca | Rebecca
1 | Melanie | Melanie | Melanie | Melanie | Melanie
2 | Caren | Caren | Caren | Caren | Caren
3 | Skye | Skye | Skye | Skye | Skye
4 | Britney | Britney | Britney | Britney | Britney
5 | Deanna | Deanna | Deanna | Deanna | Deanna
6 | Emily | Emily | Emily | Emily | Emily
7 | Mackenzie | Mackenzie | Mackenzie | Mackenzie | Mackenzie